|  |  |
| --- | --- |
| 20-Nov-15 | Full Proposal content is delivered to CCWG by 23:59 UTC |
| 21 – 23 Nov-15 | CCWG Co-Chairs and Rapporteurs gather feedback from Working Party groups, legal counsel and Advisors |
| 23-Nov-15 | CCWG final comments on Full Proposal due by 23:59 UTC |
| 24-25 Nov 15 | Back and forth and finalizing content with Co-Chairs, Writing team holding the pen |
| 25-Nov-15 | Content due to translation / formatting by 23:59 UTC |
| 30-Nov-15 | Begin Phase 2 of Consideration by Chartering Organizations |
| 30-Nov-15 | Begin professional proofreading/final editing |
| 12 -Dec-15 | Translations ready |
| 20-Dec-15 | Delivery of final proofreading/editing |
| 21-Dec-15 | End of public comment and first close for Chartering Organizations to indicate support for recommendations |
| 24-Dec-15 | Staff summary of public comments and Chartering Organization support for recommendation |